## Slide 1
Project: 2020 Q1-01 - Benson Hill Biosystems – CropOS Onboarding
Product Owner | Shailaja Suresh
Core Team | Rohit – Tech Architect .Net Saravanakumar Ganesan – Project Lead .Net Lakshmi – Project Lead Python Bhanuprathap – Python Developer Mukesh - .Net Developer
Project Description | CropOS is built to provide the data through uploading files and makes the Breed application to perform computational breeding on Cloud.
Overall Project Health (RAG) |  |  | 
Scope | Cost | Timeline | Resources
Project Progress Summary
Sprint 2020 Q1-01 from 02-Jan-2020 to 17-Jan-2020. Python – Total tasks pulled – 8 .NET – Total tasks pulled – 24
Risks/Issues | Risk Management
Foresee risks in terms of collaboration with the US counterparts and Scientists. Feature visibility for upcoming sprints may affect sprint planning in future. | Identified and nominated SPOCs for collaboration with US team members in terms of email and MOMs
Sprint Milestones (Sprint Q4-04) | Target Completion Date | % Complete
Sprint Planning | December 30, 2019 | 100%
Dev Complete Tasks (Python) – (5/8) | January 17, 2020 | 62%
Dev Complete Tasks (. Net) – (8/24) | January 17, 2020 | 33%
QA Complete Tasks (Python) – (4/8) | January 17, 2020 | 50%
QA Complete Tasks (. Net) – (0/24) | January 17, 2020 | 0%
Sprint Review | January 20, 2020 | 0%
Sprint Retrospection | January 20, 2020 | 0%
Upcoming Activities
Germplasm validation updates. File format changes in CustomMarkerSet and Genomic files. Certificate configurations for corresponding environments to make them https enabled. Additional testing on big file uploads. Code Refactor
Reference Data

## Slide 2
Project: 2020 Q1-01
- BHB – CropOS Onboarding – Quality Analysis
Root Cause Analysis
Xls format files with different content type than open excel format got rejected during upload. Added generic excel contentType to be accepted.
Severity | Open | Assigned | Fixed | Reopened | Closed | Not a Defect
Critical |  |  |  |  |  | 
High |  |  |  |  | 1 | 
Medium |  |  |  |  |  | 
Low |  |  |  |  |  | 
Total |  |  |  |  | 1 | 
Unit Testing – Defect Summary Report
Reference Data

## Slide 3
Project: 2020 Q1-01 - BHB – CropOS Onboarding – Quality Analysis_UAT
By Status |  | By Severity | 
Fixed | 0 | Critical | 0
Open | 0 | High | 0
Reopen | 0 | Medium | 0
Assigned | 0 | Low | 0
Total | 0 | Total | 0
Improvements from last sprint
Python – Created lambda function to get excel parameters to avoid download big files. .NET – Created lambda function to get custom marker values.
Root Cause Analysis
NA

## Slide 4
Project: 2020 Q1-01 - Benson Hill Biosystems – CropOS Onboarding
Action Items | Response
Python pipeline to Google cloud as POC to reduce cost. | Shailaja informed feasibility of moving one python pipeline to Google cloud from AWS is already performed by a third-party vendor suggested by Google. Any other POC work Shailaja will let us know on demand
Initial integration on new data stream. | Rohit to initiate a separate discussion with Shailaja and Jim on selecting and executing a “Initial Integration on new Data Stream from R&D” involving CES R&D team would happen on Q2, 2020.
Demo on visualization. | Lakshmi will provide the demo on 17th of January 2020 as per Shailaja request
QA talent has resigned. | Interview with Michael for Sumit Saha has happened on Dec 20th and Michael informed Joshua that Sumit Saha has been selected for QA tasks and would be under review for 30 days for confirmation. Onboarding plan was sent to Michael on 30-Dec-2019.
Michael suggested CES to provide the Coding Standard document. | Saravana sent the initial draft on 31st December and currently working on the final version. Will be provided on or before 15-January-2020.