## Q1-01
Sprint No | Card Number | Tasks in Sprint | Technology | Development | Unit Testing | UAT | Production Ready
2020 Q1-01 | CDOSCRUM-1032 | Email feature flag does not work - enabled for all users in PROD | .NET | Completed
| CDOSCRUM-1018 | Germplasm when hybrid needs validation before upload | .NET | Completed
| CDOSCRUM-577 | Review and identify remediation strategies for Security Assessment Report item 12.3 - data trasmitted over unencrypted connections | .NET
| CDOSCRUM-1053 | Germplasm when inbred needs validation change | .NET
| CDOSCRUM-1045 | As a CropOS user, I want to upload a custom marker set as a text file with file extension txt | .NET | Completed
| CDOSCRUM-1044 | As a CropOS user, when I select the dropdown on the Set Partner window, the items should be sorted alphabetically descending | .NET
| CDOSCRUM-1039 | As a CropOS user, when I create an unordered dataset, I want to see Reference Genome: None in the header of the populate dataset view | .NET
| CDOSCRUM-1038 | As a CropOS user, when I upload a hapmap file that has a tab-delimited header, I want to see an error message that identifies the issue as delimiter | .NET
| CDOSCRUM-1027 | Add secret manager access to IAM. | Python | Completed | Completed | Completed | Completed
| CDOSCRUM-1026 | Basic file validation before upload to s3 | .NET | Completed
| CDOSCRUM-1020 | Species Service | .NET
| CDOSCRUM-1019 | Partner Service | .NET
| CDOSCRUM-1017 | Research on getting the sheet names and column headers from excel for validation of germplasm and phenotype using lambda service | Python | Completed | Completed | Completed
| CDOSCRUM-1015 | GenomicDataImport test cases | .NET | Completed
| CDOSCRUM-1012 | Refactor CustomMarkerSet processing in onboarding | .NET
| CDOSCRUM-1006 | Remove temporary file download and re upload | .NET
| CDOSCRUM-992 | Remove plaintext credentials in genotype_pipeline config.config | Python | Completed
| CDOSCRUM-987 | Notifying user about active upload | .NET
| CDOSCRUM-971 | 401 errors not logged for api/CustomMarkerSet GET | .NET | Completed
| CDOSCRUM-924 | Enable https for API in PROD | .NET
| CDOSCRUM-905 | Increase code coverage of onboarding client Services | .NET | Completed
| CDOSCRUM-904 | Increase code coverage of onboarding client from 10% to 20% as measured by sonarqube | .NET | Completed
| CDOSCRUM-895 | Optimize fimputation python code to reduce execution time on large datasets | Python
| CDOSCRUM-894 | GP_CMS_Pipeline_Trigger lambdas different in DEV UAT PROD | Python | Completed | Completed | Completed | Completed
| CDOSCRUM-873 | Genotype Pipeline python code should be upgraded to python 3 prior to deprecation of 2.7 | Python | Completed | Completed | Completed | Completed
| CDOSCRUM-865 | Enabled HTTPS in UAT for Api and client by using onboarding-*.uat.crop-os.com | .NET
| CDOSCRUM-852 | Update TLS/SSL certificate for RDS connection | .NET
| CDOSCRUM-850 | Change UAT configuration to use onboarding*.uat.crop-os.com | .NET
| CDOSCRUM-842 | Implement DEV url: onboarding-client.dev.crop-os.com | .NET
| CDOSCRUM-791 | In the phenotype wide format template Germplasm Name is currently derived from "Variety", needs to be "Germplasm Name" | .NET
| CDOSCRUM-1056 | Research - review GBLUP documentation and compile a list of questions | Python
| CDOSCRUM-1025 | Genotype pipeline changes to handle large vcf files. | Python