## Bugs
On-Boarding Sprint bugs logged
Bug Artifact |  |  |  | Environment | DEV
|  |  |  | OS & Browser | Chrome
|  |  |  | Last Updated | 2020-01-03
Bug_ID(From JIRA Board) | ID | Description | Steps To Reproduce | Acceptance Criteria | Issue linked | Priority | Type | Sprint | RCA | Status | Assigned To | LoggedDate
1 Added as Comment | Bug_001 | View file is missing only for the successful uploads | 1. Go to onboarding portal 2. Populate Dataset 3. Create a new data set 4. Upload any valid germplasm | 1. User should be able to see the View file option after upload. 2. User should be able to download file from View file link | CDOSCRUM-592 | High | Regression | CDOSCRUM Sprint 2019Q3-03 | Code issue | Closed | Saravana Ganesan | 2019-09-03
2 Added as Comment | Bug_002 | Specific Error messages are not displaying, Instead "Validation Failed" is displaying for all the invalid uploads | 1. Go to Populate dataset 2. Create a new data set 3. Upload any Invalid germplasm with Dplicate ID | 1. User should be able to see the specific error message in Progress section. | CDOSCRUM-592 | High | Regression | CDOSCRUM Sprint 2019Q3-03 | Code issue | Closed | Saravana Ganesan | 2019-09-03
3 Added as Comment | Bug_003 | Species and Imports Completed missing record for each dataset from dataset history. | 1. Select the partner 2. Go to Dataset Status and notice the issue. | 1. User should be able to view the dataset history with all the existing records. | CDOSCRUM-360 | High | Regression | CDOSCRUM Sprint 2019Q3-03 | Code issue (Impacted due to disassemble of functionalities from monolithic individual call to multiple api calls) | Closed | Saravana Ganesan | 2019-08-21
4 Added as Comment | Bug_004 | By default dataset history should be ordered by name is resolved. | 1. Select the partner 2. Go to Dataset Status and notice the issue. | 1. User should be able to see the ordered dataset name | CDOSCRUM-360 | High | Regression | CDOSCRUM Sprint 2019Q3-03 | Code issue | Closed | Saravana Ganesan | 2019-08-23
5 Added as Comment | Bug_005 | Even when clicked on Remove, Line item doesnot get erased from the Progress section | 1. Upload any file for any dataset 2. Click on remove Notice after 30 secs that line item again display in the progress section. | 1. User should not see the line item once clicked on Remove 2. When user come back to the dataset he should not see the item which is removed already. | CDOSCRUM-741 | High | Regression | CDOSCRUM Sprint 2019Q3-03 | Code issue | Closed | Saravana Ganesan | 2019-09-05
6 Added as Comment | Bug_006 | In Dev if the file upload has failed in processing or validation we see the actual error message but after 30 sec the specific error message is changed to "Onboarding Failed." | 1. Upload any invalid file Notice after 30 sec the appropriate error messge is replaced with "validation Failed" | User should see the appropriate error message evevry time it should not change to "Validatio Failed" or "Onboarding Failed" | CDOSCRUM-592 | High | Regression | CDOSCRUM Sprint 2019Q3-04 | The actual error message was not getting saved, a very generic message "validationFailed" or "OnboardingFailed" was replaced to actual exception message. | Closed | Saravana Ganesan | 2019-09-06
CDOSCRUM-751 | Bug_007 | In Dev if the upload is canceled Notice After a while the upload again shows up as in process. | 1. Upload any file for any dataset 2. Click on Cancel Notice after 30 secs that line item again display in the progress section. | User should not see the line item again if upload is canceled. | CDOSCRUM-592 | High | Regression | CDOSCRUM Sprint 2019Q3-04 | Cancel functionality was not updating any status to the database. As a fix, this functionality completely handled. | Closed | Saravana Ganesan | 2019-09-06
CDOSCRUM-796 | Bug_008 | Console Error for using JQuery code for signalR even though we had angular SignlaR | 1.Open Devtool 2.Select partner. Notice. console display the error message. | User should not see the console error in Devtool | NA | High | Regression | CDOSCRUM Sprint 2019Q3-04 | Jquery Compatibility error | Closed | Mukesh | 2019-09-23
CDOSCRUM-783 | Bug_009 | Uploaded file not appearing in Completed section automatically. | Upload any file and wait | Once the file is uploaded successfully it should automatically go to completed section. | NA | High | Regression | CDOSCRUM Sprint 2019Q3-04 | Realtime database update was not working as expected. NoTrace logic implemented to get this working as expected. | Closed | Rohit | 2019-09-17
Added as a comment | Bug_010 | Issue1 : Export button is not responding. | Click on Export | Export button should display excel and word option to export the dataset details. | CDOSCRUM-781 | Medium | Regression | CDOSCRUM Sprint 2019Q3-04 | Popper.js dependency failed after bootstrap update | Closed | Mukesh | 2019-09-17
Added as a comment | Bug_011 | Issue2 : Custom Marker set name Functionality not working. | Click on Custome marker set button | When Custom marker button is clicked name popup should appear. | CDOSCRUM-781 | Medium | Regression | CDOSCRUM Sprint 2019Q3-04 | Popper.js dependency failed after bootstrap update | Closed | Mukesh | 2019-09-17
Added as a comment | Bug_012 | Prepend exclamatory warning icon for error message in populate dataset. Prepend the icons for different status in dataset history – just like before. | open populate data set and dataset history | Icon should be similar to previous version | CDOSCRUM-782 | Medium | Regression | CDOSCRUM Sprint 2019Q3-04 | Bootstrap update removed the glyphicons. Implemented Font awesome | Closed | Mukesh | 2019-09-18
Added as a comment | Bug_013 | Change the font size to previous version | open populate data set and dataset history | Font size should be similar | CDOSCRUM-782 | Medium | Regression | CDOSCRUM Sprint 2019Q3-04 | Default font size of newer version of bootstrap differed | Closed | Mukesh | 2019-09-19
Added as a comment | Bug_014 | In DEV if the genotype or phenotype file is uploaded Notice The status for the pipeline shows in plain text. | 1. Upload any phenotype or genotype file Notice the status shows in plain text. | The status for phenotype and genotype pipeline processing should be same as previous (in blue text with icons) | CDOSCRUM-833 | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Mukesh | 2019-10-08
CDOSCRUM-832 | Bug_015 | View logs for downloading vcf validator logs are not displayed. | 1. Upload germplasm 2. Upload Invalid genotype file which fails at first step in PIpeline. | The genotype pipeline failed at any step should display view log error in Status which should download log when clicked. | CDOSCRUM-832 | High | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed |  | 2019-10-08
CDOSCRUM-833 | Bug_016 | Phenotype files not displaying as processing when uploaded | 1.Upload a germplasm and then phenotype file Observe that the file does not appear in the processing section but in the backend we can see the file is processing. | Phenotype files should display as processing when uploaded | CDOSCRUM-833 | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed |  | 2019-10-08
Added as a comment | Bug_017 | Phenotype count tab should display for Experiments, and Phenotype Measures as new at second upload. And should use the same logic as phenotypes | 1.Upload a germplasm and then phenotype file 2. Upload again phenotype for second time Observe that the Experiments, and Phenotype Measures appear as new for second upload. | Phenotype count tab should display Experiments, and Phenotype Measures as updated at second upload. | CDOSCRUM-752 | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Saravana | 2019-10-10
Added as a comment | Bug_018 | Getting Console error at Create dataset | 1. Go to dashboard 2. click on create 3.when both name and species fields are not provided and unordered Dataset radio button is selected. | There should be no Console error and data set should be created successfully | CDOSCRUM-835 | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Mukesh | 2019-10-15
Added as a comment | Bug_019 | Ordered dataset is created without reference genome | 1. Enter Name and species 2. Select Unordered and then Ordered dataset 3. Click on save. | Save button should be disabled, If user switch between ordered and Unordered. | CDOSCRUM-835 | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 | Scenario came out of the feature not given as requirement | Closed | Mukesh | 2019-10-15
Informed on Skype | Bug_020 | Files are not downloading | 1. Go to any data set 2. Select any file from the completed section 3. Click on it. | Files should download |  | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Rohit | 2019-10-16
Informed on Skype | Bug_021 | "You are using an outdated browser. Please update to a modern browser for better experience." Is shown wrongly (in dev Chrome). Also Cards are not flipping | 1. Go to DEV 2. Select partner | Banner should not be displayed in Chrome |  | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Rohit | 2019-10-17
Added as a comment | Bug_022 | ”Select dataset dropdown,Create and Rename” getting disabled after the error message for vcf upload is displayed. | 1.Upload a germplasm and then VCF (which should have some germplasm Id matching) | All the three options (select dataset dropdown, create button and rename) should enable after the upload. | CDOSCRUM-834 | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Saravana | 2019-10-18
CDOSCRUM-857 | Bug_023 | Genotype Pipeline are failing immediately after uploading .gz(zipped files) | Create a dataset (Unordered or Ordered) Upload germplasm Upload zipped genotype file (vcf.gz) Notice Immediately after uploading file, the pipeline is failing and the status doesnot change in Onboarding portal. | Genotype file with .gz extension should be uploaded successfully and pipeline should be succeeded | CDOSCRUM-834 | High | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Saravana | 2019-10-21
Added as a comment | Bug_024 | File with not required headers which are Season, RepNo , Entry #, Plot #, Range, Row, and Variety are not uploading | Create a dataset (Unordered or Ordered) Upload germplasm Upload Phenotype wideformat file with not required headers Notice the error message appears and file does not upload | File should get uploaded if non required headers are missing. | CDOSCRUM-851 | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Saravana | 2019-10-22
Informed on Skype | Bug_025 | Phenotype pipelines are failing | Create a dataset (Unordered or Ordered) Upload germplasm Upload Phenotype Notice the Pipelines are failing | Pipeline should get succeded for the valid phenotype upload |  | Medium | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Closed | Bhanu/Lakshmi | 2019-10-22
Informed on Skype | Bug_026 | Latest upload not appearing at top in progress section. | Create a dataset (Unordered or Ordered) Upload germplasm Upload Phenotype Notice the upload in progress section is not showing at the top. | Latest upload should be on top. |  | Low | Regression | CDOSCRUM Sprint 2019Q4-01 |  | Open | Saravana | 2019-10-23
CDOSCRUM-901 | Bug_027 | Germplasm and Phenotype files with count generated throws error | 1.Create a dataset (Unordered or Ordered) 2.Upload germplasm Upload Phenotype 3.Download the germplasm & phenotype file from onboarding 4.Try uploading them Notice the error message during upload. | Files with count tab/sheet should get uploaded with successfull message instead of error message. | CDOSCRUM-752, 851 | Low | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Saravana | 2019-11-05
CDOSCRUM-912 | Bug_028 | In DEV, Instructions and Templates are not downloading from the onboarding dashboard. | 1.Go to DEV Onboarding 2.Click on the Instruction and Templates 3.Try downloading any file from the above tabs. Notice Error is thrown | Files should download sucessfully. |  | Medium | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Rohit | 2019-11-06
Add as a comment | Bug_029 | In DEV completed section grid is misaligned. | 1.Go to DEV Onboarding 2.Select any dataset Notice the completed section is misaligned. | Completed section should be aligned | CDOSCRUM-917 | Medium | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Mukesh | 2019-11-07
Added as a comment | Bug_030 | In DEV ,the New and Updated Columns are chopping off from the history | 1.Go to DEV Onboarding 2.Go to Dataset history Notice The New and Updated Columns are chopping off from the history | The New and Updated Columns should appear as previously | CDOSCRUM-917 | Medium | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Mukesh | 2019-11-13
Added as a comment | Bug_031 | Germplasm with no data when uploaded got stuck in processing state. | 1.Go to DEV Onboarding 2.Select any dataset 3. Upload the germplasm with no data Notice Firstly the error message appears but after one min it started processing again and gets stuck processing state. | The upload should display the correct error message | CDOSCRUM-826 | Medium | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Mukesh | 2019-11-13
Informed on Skype | Bug_032 | Genotype Pipeline is triggering twice with same onboarding ID with the interval of 4 min | 1.Go to DEV Onboarding 2.Select any dataset 3. Upload the germplasm 4. Upload genotype file Notice Genotype Pipeline is triggering twice with same onboarding ID with the interval of 4 min | Genotype Pipeline should be triggered only once for one onboarding id | CDOSCRUM-887 | High | Regression | CDOSCRUM Sprint 2019Q4-02 | Inconsistent bug | Open | Lakshmi | 2019-11-11
Informed on Skype | Bug_033 | Console displaying "Error during WebSocket handshake: Unexpected response code: 400" | 1.Go to DEV Onboarding 2.Select any partner 3.open Dev tool (F12) Notice Error during WebSocket handshake: Unexpected response code: 400 | Console should not be displayed | CDOSCRUM-887,917 | Low | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Mukesh | 2019-11-12
CDOSCRUM-954 | Bug_034 | Duplicate germplasms are inserted into the database and display following Error message "Sequence contains more than one matching element" during upload | 1. Go to DEV Onboarding 2. Select partner 3. Upload germplasm 4. Again upload the same germplasm Notice Error during germplasm upload | Germplasm should get uploaded without throwing duplication germplasm Id's error message |  | Medium | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Rohit | 2019-11-15
Added as a comment | Bug_035 | On data set change there is a uploader queue being cleared. | 1.Go to DEV Onboarding 2.Select any partner 3.Upload any file 4.Then change dataset and revisit on same dataset Notice the upload is getting canceled. | we should disable the select existing dataset dropdown when file is uploading. or let the user know this will cancel the operation. | CDOSCRUM-887,919 | Medium | Regression | CDOSCRUM Sprint 2019Q4-02 |  | Closed | Mukesh | 2019-11-14
Informed on skype | Bug_036 | Germplasm Upload is throwing error "An error occurred while updating the entries. See the inner exception for details." | 1.Go to UAT Onboarding 2.Select any partner 3.Upload any germplasm file Notice the upload is getting error. | Germplasm upload should be successfull. | In UAT | High | Regression | CDOSCRUM Sprint 2019Q4-03 | Entity framework package issue. Fixed. | Closed |  | 2019-12-02
CDOSCRUM-1009 | Bug_037 | Export file and download file are throwing error. | 1.Go to DEV Onboarding 2.Select any partner 3.Upload any file Notice the download is getting error. | All the files should download and export successfully. | CDOSCRUM-1009 | High | Regression | CDOSCRUM Sprint 2019Q4-03 | Authorization failure. Updated the scope of the request to get this resolved. | Closed |  | 2019-12-09
Informed on skype | Bug_038 | Genotype pipleine failing for all the uploads and status is not updating in the completed section. | 1.Go to DEV Onboarding 2.Select any partner 3.Upload any genotype file Notice the uplaod pipeline is failing. | All the genotype files should be uploaded successfully and the pipeline should get succeeded. | CDOSCRUM-1001 | High | Regression | CDOSCRUM Sprint 2019Q4-03 | Impact of genomic refactor for scalability. Updated code. | Closed |  | 2019-12-10
Informed on skype | Bug_039 | Hmp uploads are failing at vcfvalidator pipeline and Error log is not downloading. | 1.Go to DEV Onboarding 2.Select any partner 3.Upload any genotype file which fails at validator step Notice the error log is not downloading . | Error log should get downloaded. | CDOSCRUM-1001 | High | Regression | CDOSCRUM Sprint 2019Q4-03 | Impact of genomic refactor for scalability. Updated code. | Closed |  | 2019-12-11
Added as a comment | Bug_040 | .xls files are not getting uploaded for germplasm and phenotype data upload | 1.Go to DEV Onboarding 2.Select any partner 3.Upload .xls file for germplasm and phenotype. | file should be uploaded for further processing. | CDOSCRUM-1026 | High | Regression | CDOSCRUM Sprint 2020Q1-01 | Xls format files with different content type than open excel format got rejected during upload. Added generic excel contentType to be accepted. | Closed | Saravana | 2019-12-31

## Unit_TestDefect 2020 Q1-01
Severity | Open | Assigned | Fixed | Reopend | Closed | Not a defect
Critical
High |  |  |  |  | 1
Medium
Low
Total bugs in Q3_Sprint 04 |  |  |  |  | 1

## Unit_TestDefect Q3 Sprint_0_1
Severity | Open | Assigned | Fixed | Reopend | Closed | Not a defect
Critical
High |  |  |  |  | 4
Medium |  |  |  |  | 4
Low
Total bugs in Q3_Sprint 04 |  |  |  |  | 8

## Unit_TestDefect Q4 Sprint_01
Severity | Open | Assigned | Fixed | Reopened | Closed | Not a defect
Critical
High |  |  |  |  | 2
Medium |  |  |  |  | 10
Low |  |  |  |  | 1
Total bugs in Q4_Sprint 01 |  |  |  |  | 13

## Unit_TestDefect Q4 Sprint_02
Severity | Open | Assigned | Fixed | Reopened | Closed | Not a defect
Critical
High | 1
Medium | 2 |  |  |  | 2
Low |  |  |  |  | 2
Total bugs in Q4 _Sprint 02 | 7

## Unit_TestDefect Q4 Sprint_0_3
Severity | Open | Assigned | Fixed | Reopened | Closed | Not a defect
Critical
High |  |  |  |  | 4
Medium
Low
Total bugs in Q4 _Sprint 03 | 4